## Project Details
Project ID | Project Name | Project Status | App Name | Project Start Date | Project End Date (Expected) | Business Owner | Application Owner | Development Owner | Testing Owner | Support Owner
P0001 | Changes in Demo E-Commerce Website (Demoblaze) | Open | Demoblaze | 2025-06-01 | 2025-06-30 | Jameer | Naresh | Siddharth | Vijay | Rajesh

## Test Plan
Test Plan Section | Details
Project Name | Changes in Demo E-Commerce Website (Demoblaze)
App Name & URL | Demoblaze, https://www.demoblaze.com/
Objective | Validate the core functionalities (Login, Logout, Cart, Checkout)
Test Scope | Functional Testing
Test Strategy | Manual Testing
Number of resources | 1
Test Environment | Windows 11, Chrome, Edge, Firefox
Tools Used | Excel for Test Cases, Jira for Bug Tracking, Jira for project management
Entry Criteria | Application is deployed in QC Environment, Unit testing and system integration testing is completed with no high-priority bugs open.
Exit Criteria | All test cases executed. All major test cases passed with no high-priority defects open.
Risks & Mitigation | Browser compatibility issues → Test on multiple browsers
Roles & Responsibilities | Tester: Vijay
Testing Start Date | 2025-06-20
Testing End Date (Expected) | 2025-06-25

## Test Scenarios
Test Scenario ID | App Name | Menu | Test Scenario Desc | Drafted On | Drafted By
TS0001 | Demoblaze | Sign up | To verify Signup functionality in Demoblaze. | 2025-06-21 | Vijay
TS0002 | Demoblaze | Log in | To verify login functionality in Demoblaze. | 2025-06-21 | Vijay
TS0003 | Demoblaze | Forgot Password | To verify forgot password functionality in Demoblaze. | 2025-06-21 | Vijay
TS0004 | Demoblaze | Log out | To verify logout functionality in Demoblaze. | 2025-06-21 | Vijay
TS0005 | Demoblaze | Home | To verify the homepage and navigation functionality. | 2025-06-21 | Vijay
TS0006 | Demoblaze | Home | To verify product listing and category filtering. | 2025-06-21 | Vijay
TS0007 | Demoblaze | Product Page | To verify product details page functionality. | 2025-06-21 | Vijay
TS0008 | Demoblaze | Cart | To verify shopping cart functionality. | 2025-06-21 | Vijay
TS0009 | Demoblaze | Cart | To verify checkout and order placement functionality. | 2025-06-21 | Vijay
TS0010 | Demoblaze | Cart | To verify payment processing and order confirmation. | 2025-06-21 | Vijay
TS0011 | Demoblaze | Entire Website | To verify responsiveness and compatibility across different devices and browsers. | 2025-06-21 | Vijay
TS0012 | Demoblaze | Entire Website | To verify security aspects of the application. | 2025-06-21 | Vijay
TS0013 | Demoblaze | Entire Website | To verify user session management. | 2025-06-21
TS0014 | Demoblaze | Entire Website | To verify website performance under different load conditions. | 2025-06-21 | Vijay

## Test Cases
User Type | App Name | Menu | Test Scenario Desc | Test Case ID | Test Case Desc | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail/Hold) | Created On | Executed On | Defect Id (If Any) | Iteration (First/Second/Third) | Remark | Tested By
General Login | Demoblaze | Sign up | To verify Signup functionality in Demoblaze. | TC0001 | Verify that a new user can register with valid credentials. | Navigate to the Demoblaze website. Click on 'Sign up' button. Enter a unique username. Enter a valid password. Click on the 'Sign up' button. Verify that a success message appears. | User Name: Test1 Pwd: Test1@2025 | System should allow new user to register with valid credentials. | System is allowing new user to register with valid credentials. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Sign up | To verify Signup functionality in Demoblaze. | TC0002 | Verify that an error message appears when trying to register with an existing username. | Navigate to the Demoblaze website. Click on 'Sign up' button. Enter an existing username. Enter a valid password. Click on the 'Sign up' button. Verify that an error message appears. | User Name: Test1 Pwd: Test1@2025 | System should not allow to register with an existing username. | System is allowing to register with an existing username eventhough the same username present in the system with active status. --> 21-June-2025 It is working fine now. System is not allowing to register with an existing username. While clicking on register button, it is giving error msg. "Username already exist in the system". --> 24-June-2025 | Pass | 2025-06-21 | 2025-06-24 | D0001 | Second | It was failed on 22-June-2025 and after defect closer retested on 24-June-2025. | Vijay
General Login | Demoblaze | Sign up | To verify Signup functionality in Demoblaze. | TC0003 | Verify that an error message appears when trying to register with an empty username or password. | Navigate to the Demoblaze website. Click on 'Sign up' button. Leave the username field blank. Enter a valid password. Click on the 'Sign up' button. Verify that an error message appears. | N/A | System should not allow to register and an error should display i.e. "Username and password should not be blank". | System is not allowing registration with an existing username (which is correct), but instead of showing a proper error message, it displays only a generic message: 'Error' in red --> 21-June-2025 | Pass | 2025-06-21 | 2025-06-24 | D0002 | Second | It was failed on 22-June-2025 and after defect closer retested on 24-June-2025. | Vijay
General Login | Demoblaze | Sign up | To verify Signup functionality in Demoblaze. | TC0004 | Verify that special characters are not allowed in the username field. | Navigate to the Demoblaze website. Click on 'Sign up' button. Enter a username with special characters. Enter a valid password. Click on the 'Sign up' button. Verify that an error message appears. | User Name: Test1 Pwd: Test1@2025 | System should not allow special characters in the username field. | System is not allowing to enter special characters in the username field. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0005 | Verify that a user can log in with valid credentials. | Navigate to the Demoblaze website. Click on 'Log in' button. Enter a valid username. Enter a valid password. Click on the 'Log in' button. Verify that the user is successfully logged in. | User Name: Test1 Pwd: Test1@2025 | System should allow user to log in with valid credentials. | The user is successfully logged in and redirected to the homepage with the login option replaced by the user’s name in the header. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0006 | Verify that an appropriate error message appears when logging in with an incorrect username/password. | Navigate to the Demoblaze website. Click on the "Log in" button. Enter an incorrect username in the username field. Enter an incorrect password in the password field. Click on the "Log in" button. Verify that an appropriate error message (e.g., "User does not exist" or "Incorrect password") is displayed. | User Name: Test1 Pwd: Test1@2025 | System should show an error message "Invalid username or password. Please try again" when logging in with an incorrect username/password. | The system displays a clear and user-friendly error message, such as: “Invalid username or password. Please try again.” The user remains on the login form. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0007 | Verify that the login session persists after page refresh. | Navigate to the Demoblaze website. Click on the "Log in" button. Enter a valid username and valid password. Click on the "Log in" button. Verify that the user is successfully logged in (e.g., username appears in the header). Refresh the webpage using Ctrl + R or the browser refresh button. Verify that the user remains logged in and does not need to re-enter credentials. | User Name: Test1 Pwd: Test1@2025 | User should remain logged in and the session information (username in the header) should be retained. | After refreshing the page, the user remains logged in and the session information (username in the header) is retained. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0008 | Verify that the session remains active after logging in. | Log in to the Demoblaze website with valid credentials. Perform various actions (e.g., navigate pages, add items to cart, check profile). Verify that the session remains active without requiring re-login. | User Name: Test1 Pwd: Test1@2025 | Session should remain active across multiple page navigations and interactions until explicitly logged out or the session times out. | The session remains active across multiple page navigations and interactions until explicitly logged out or the session times out. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0009 | Verify that the session expires after a defined period of inactivity. | Log in to the Demoblaze website with valid credentials. Remain inactive for the defined timeout period. Try performing an action (e.g., navigating to a different page). Verify that the session has expired and the user is redirected to the login page or shown a session timeout message. | User Name: Test1 Pwd: Test1@2025 | The user should automatically logged out and redirected to the login/home page after the defined inactivity period (15 minutes). | After the defined inactivity period (15 minutes), the user is automatically logged out and redirected to the login/home page. A message may indicate session timeout. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0010 | Verify that a logged-in user’s name is displayed in the header. | Log in to the Demoblaze website with valid credentials. Verify that the username appears in the header, confirming a successful login. | User Name: Test1 Pwd: Test1@2025 | System should display a logged-in user’s name in the header. | Upon successful login, the user’s registered username is displayed in the header in place of the "Log in" link. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0011 | Verify Browser History and Credential Clearance on Relogging | 1. Log in to the application using valid credentials. 2. Navigate through different pages of the application. 3. Log out of the application. 4. Immediately attempt to log in again by accessing the login page. | User Name: Test1 Pwd: Test1@2025 | 1. The browser history related to the previous session should be cleared. 2. The login page should not autofill or suggest the previously used username and password. 3. The user must enter the credentials manually to log in again. | After logging out and clearing browser cache or using private/incognito mode, previous session credentials are not auto-fill or persist. Login page appears clean. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log in | To verify login functionality in Demoblaze. | TC0012 | Verify that the website loads within acceptable time limits under normal conditions. | Open the Demoblaze website in a web browser. Measure the page load time using browser developer tools or a timer. Verify that the website loads within the defined acceptable time limit (e.g., under 3 seconds). | User Name: Test1 Pwd: Test1@2025 | The website should loads completely within 2–3 seconds under standard network conditions, and all UI components render correctly. | The website loads completely within 2–3 seconds under standard network conditions, and all UI components render correctly. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Forgot Password | To verify forgot password functionality in Demoblaze. | TC0013 | Verify that a forgot password option is available in the login | Navigate to the Demoblaze login page. Check if a 'Forgot Password' option is present. Verify that clicking on it redirects to the password recovery process. |  | Forgot password option should be available in the login page. | A “Forgot Password” link is displayed below the login form. Clicking the link redirects to the password reset page. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Forgot Password | To verify forgot password functionality in Demoblaze. | TC0014 | Verify that an old passwords are not allowed while password reset using forgot password option. | Navigate to the Demoblaze login page and click on "Forgot Password". Enter the registered email/username and follow the password reset process. Try setting the old password as the new password. Verify that an error message appears (e.g., "You cannot use a previously used password."). | User Name: Test1 Pwd: Test1@2025 | The system should not allow the user to reset the password using their existing/old password. A clear error message should be displayed. | After entering the current password in the reset form, the system displays an error message: “New password cannot be the same as the previous password.” Password reset is blocked until a different password is entered. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Forgot Password | To verify forgot password functionality in Demoblaze. | TC0015 | Verify that a user is able to reset password using forgot password option with a Password changed successfully. | Navigate to the Demoblaze login page and click on "Forgot Password". Enter the registered email/username and submit the request. Follow the password reset instructions received via email/SMS. Set a new password and confirm the change. Verify that a success message appears (e.g., "Password changed successfully."). Log in with the new password to confirm the change. | N/A | User should be able to successfully reset the password, and the system should display a message confirming that the password has been changed. | Upon submission, a confirmation message “Your password has been changed successfully.” is displays, and the user has redirected to the login page. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Forgot Password | To verify forgot password functionality in Demoblaze. | TC0016 | Verify that a user is able to login with new password after reset using forgot password option. | eset the password using the "Forgot Password" option. Navigate to the Demoblaze login page. Enter the registered username/email and the new password. Click on the "Log in" button. Verify that the login is successful and the username appears in the header. | User Name: Test1 Pwd: Test001@2025 | User should be able to log in successfully using the newly set password. The old password should not be accepted. | Login with the new password is successful. Attempt to log in with the old password resulted in an error message: “Invalid username or password.” | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log out Menu | To verify logout functionality in Demoblaze. | TC0017 | Verify that clicking on the logout button logs the user out successfully. | Log in to the Demoblaze website with valid credentials. Click on the "Log out" button. Verify that the user is redirected to the homepage or login page. Confirm that the username is no longer displayed in the header. Try accessing a restricted page and verify that it prompts for login. | UserName: Test03 Pwd: Test03@2025 | Clicking the logout button should terminate the user session and log the user out. | Logout button click logs out the user and session is cleared. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log out Menu | To verify logout functionality in Demoblaze. | TC0018 | Verify that clicking “Logout” ends the session and redirects to the homepage. | Log in to the Demoblaze website with valid credentials. Click on the "Log out" button. Verify that the session ends and the user is redirected to the homepage. Confirm that the username is no longer visible in the header. Attempt to access a restricted page and ensure it prompts for login. | UserName: Test03 Pwd: Test03@2025 | After logout, session should end and user should be redirected to the homepage. | After logout, session ends and homepage is loaded. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log out Menu | To verify logout functionality in Demoblaze. | TC0019 | Verify that the browser “Back” button does not reopen a session after logout. | Log in to the Demoblaze website with valid credentials. Click on the "Log out" button. Verify that the session ends and the user is redirected to the homepage or login page. Press the browser "Back" button. Verify that the session does not reopen and the user remains logged out. Confirm that accessing any restricted page prompts for login again. | UserName: Test03 Pwd: Test03@2025 | Using the browser back button after logout should not restore the session or grant access to restricted content. | Browser back button does not reopen session; restricted content is not accessible. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log out Menu | To verify logout functionality in Demoblaze. | TC0020 | Verify that a logged-out user cannot access restricted pages (e.g., cart, order placement). | Log in to the Demoblaze website with valid credentials. Click on the "Log out" button to end the session. Try accessing restricted pages such as: Cart Order placement/Checkout User profile (if available) Verify that the system redirects to the login page or displays an appropriate message (e.g., "Please log in to continue."). | UserName: Test03 Pwd: Test03@2025 | After logout, user should not be able to access the cart or place orders without logging in again. | Logged-out user is prevented from accessing cart and place order functionality. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Log out Menu | To verify logout functionality in Demoblaze. | TC0021 | Verify that after logging out, the login button appears again in the website welcome screen headers. | Log in to the Demoblaze website with valid credentials. Click on the "Log out" button to end the session. Verify that the "Log in" button reappears in the website header. Ensure that the previous username is no longer displayed. | UserName: Test03 Pwd: Test03@2025 | After logout, the login button should reappear in the header replacing the username. | Login button is displayed again in the header after logout. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Home | To verify the homepage and navigation functionality. | TC0022 | Verify that the homepage loads with a list of products. | Navigate to the Demoblaze website homepage. Verify that the page loads successfully without errors. Check that a list of products is displayed on the homepage. Ensure that each product has a name, image, and price. | UserName: Test02 Pwd: Test02@2025 | Homepage should load successfully and display a grid/list of products with name, image, and price. | Homepage loads correctly and displays product grid with name, image, and price details. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Home | To verify the homepage and navigation functionality. | TC0023 | Verify that the navigation bar has functional links (Home, Contact, About us, Cart, etc.). | Navigate to the Demoblaze website homepage. Locate the navigation bar and check for the following links: Home Contact About us Cart Log in / Sign up (if applicable) Click on each link and verify that it redirects to the correct page. Ensure there are no broken links or errors. | UserName: Test02 Pwd: Test02@2025 | Navigation bar links should be visible and functional; clicking should redirect to the corresponding section/page. | All navigation links are functional and redirect to their respective pages as expected. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Home | To verify the homepage and navigation functionality. | TC0024 | Verify that clicking on “Home” redirects to the homepage. | Navigate to the Demoblaze website. Click on the "Home" button in the navigation bar. Verify that the user is redirected to the homepage. Ensure that the homepage loads correctly with products displayed. | UserName: Test02 Pwd: Test02@2025 | Clicking on the “Home” link should load the homepage with the default product list view. | Clicking on “Home” reloads the homepage and displays the default product list. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Home | To verify the homepage and navigation functionality. | TC0025 | Verify that the website is displayed properly across different screen resolutions. images and buttons resize properly when changing the screen size. | Open the Demoblaze website on a desktop browser. Resize the browser window manually or use developer tools (F12 → Toggle Device Toolbar). Test the website on different screen resolutions (e.g., 1920x1080, 1366x768, 768x1024, 375x667). Verify that: The layout adjusts correctly without overlapping elements. Images and buttons resize properly and remain functional. The navigation menu is accessible on all screen sizes. Repeat the test on a mobile device or tablet to ensure responsiveness. | UserName: Test02 Pwd: Test02@2025 | Website layout should adjust based on screen size; all elements (images, text, buttons) should resize and align correctly. | Website content adapts properly to different resolutions and elements scale responsively on screen resize. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Home | To verify product listing and category filtering. | TC0026 | Verify that all product categories (Phones, Laptops, Monitors) are displayed correctly. | Navigate to the Demoblaze website homepage. Locate the product categories section. Verify that the following categories are displayed: Phones Laptops Monitors Click on each category and ensure that relevant products are displayed correctly. Check that product images, names, and prices are visible and properly aligned. | UserName: Test02 Pwd: Test02@2025 | Category section should show all three categories: Phones, Laptops, and Monitors. | In the category section, only the 'Phones' category is displayed three times. 'Laptops' and 'Monitors' categories are missing. --> 22-06-2025 All three product categories are displayed clearly in the sidebar. --> 24-06-2025 | Pass | 2025-06-21 | 2025-06-22 | D0003 | Second | It was failed on 22-June-2025 and after defect closer retested on 24-June-2025. | Vijay
General Login | Demoblaze | Home | To verify product listing and category filtering. | TC0027 | Verify that selecting a category filters and displays only relevant products. | Navigate to the Demoblaze website homepage. Click on a product category (Phones, Laptops, or Monitors). Verify that only products from the selected category are displayed. Ensure that unrelated products are not shown. Repeat the process for each category to confirm proper filtering. | UserName: Test02 Pwd: Test02@2025 | Selecting a category should display only the products belonging to that category. | On category selection, only relevant products load as per the chosen category. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Home | To verify product listing and category filtering. | TC0028 | Verify that the pagination buttons work correctly for browsing multiple pages of products. | Navigate to the Demoblaze website homepage. Check if multiple pages of products are available. Click on the Next button and verify that the next set of products is displayed. Click on the Previous button and ensure it navigates back to the previous page. Verify that clicking on a specific page number loads the correct product list. Ensure that pagination works smoothly without errors or page load issues. | UserName: Test02 Pwd: Test02@2025 | Clicking “Next” and “Previous” should navigate between product pages and update the product list. | Pagination buttons work correctly and product list updates on page navigation. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Product | To verify product details page functionality. | TC0029 | Verify that clicking on a product redirects to the product details page. | Navigate to the Demoblaze website homepage. Select any product from the displayed list. Click on the product name or image. Verify that the user is redirected to the product details page. Ensure that the product details page displays the correct image, name, description, and price. | UserName: Test04 Pwd: Test04@2025 | Clicking a product should open its detailed view with full product information. | Product click opens the product details page with correct layout. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Product | To verify product details page functionality. | TC0030 | Verify that the product name, image, price, and description are displayed correctly. | Navigate to the Demoblaze website homepage. Click on any product to open the product details page. Verify that the following details are correctly displayed: Product Name Product Image Price Description Ensure that the details match the selected product. Check that the image is clear, properly aligned, and not broken. | UserName: Test04 Pwd: Test04@2025 | Product details page should show the correct name, image, price, and description of the selected product. | Product description does not change according to the selected product. The same description appears for all products, while name, image, and price are correctly displayed --> 22-06-2025 Now the product name, image, price, description displays correctly for the selected product. --> 24-06-2025 | Pass | 2025-06-21 | 2025-06-24 | D0004 | Second | It was failed on 22-June-2025 and after defect closer retested on 24-June-2025. | Vijay
General Login | Demoblaze | Product | To verify product details page functionality. | TC0031 | Verify that the “Add to Cart” button is functional. | Navigate to the Demoblaze website homepage. Click on a product to open its product details page. Locate and click the "Add to Cart" button. Verify that a confirmation message appears (e.g., "Product added to cart successfully."). Open the Cart page and confirm that the selected product is listed correctly. | UserName: Test04 Pwd: Test04@2025 | Clicking “Add to Cart” should add the product to the cart and confirm the action. | “Add to Cart” button adds the product and shows confirmation alert. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Product | To verify product details page functionality. | TC0032 | Verify that the browser back button returns to the product listing page. | Navigate to the Demoblaze website homepage. Click on a product to open its product details page. Press the browser "Back" button. Verify that the user is returned to the product listing page (homepage or selected category). Ensure that the previously displayed products remain visible and the page state is maintained. | UserName: Test04 Pwd: Test04@2025 | Clicking the browser back button from the product details page should return the user to the product listing page. | Browser back button takes the user back to the product listing as expected. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify shopping cart functionality. | TC0033 | Verify that a user can add a product to the cart. | Navigate to the Demoblaze website homepage. Click on a product to open its product details page. Click the "Add to Cart" button. Verify that a confirmation message appears (e.g., "Product added to cart successfully."). Open the Cart page and check if the added product is listed correctly with the correct name, price, and quantity. | User Name: Test1 Pwd: Test1@2025 | Product should be added to the cart and listed with its name and price. | After clicking on 'Add to Cart', the system shows a success message and updates the cart counter (e.g., '1'), but the product details do not appear on the cart page. --> 22-06-2025 Not the selected product displays in the cart with correct name and price. --> 24-06-2025 | Pass | 2025-06-21 | 2025-06-24 | D0005 | Second | It was failed on 22-June-2025 and after defect closer retested on 24-June-2025. | Vijay
General Login | Demoblaze | Cart | To verify shopping cart functionality. | TC0034 | Verify that the product remains in the cart after refreshing the page. | Navigate to the Demoblaze website homepage. Click on a product to open its product details page. Click the "Add to Cart" button. Open the Cart page and confirm that the product is listed. Refresh the page. Verify that the product is still present in the cart with the correct name, price, and quantity. | User Name: Test1 Pwd: Test1@2025 | Cart should retain added product after refreshing the page. | Cart retains the product and reloads it correctly after refresh. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify shopping cart functionality. | TC0035 | Verify that multiple products can be added to the cart. | Navigate to the Demoblaze website homepage. Select and click on the first product to open its product details page. Click the "Add to Cart" button and verify the confirmation message. Repeat steps 2-3 for additional products. Open the Cart page and verify that all added products are listed correctly with their names, prices, and quantities. | User Name: Test1 Pwd: Test1@2025 | User should be able to add multiple products and all should be listed in the cart. | Multiple products appear in the cart with correct name and price. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify shopping cart functionality. | TC0036 | Verify that a user can remove an item from the cart. | Navigate to the Demoblaze website homepage. Add a product to the cart by clicking the "Add to Cart" button on the product details page. Open the Cart page. Click the "Delete" or "Remove" button next to the product. Verify that the product is removed from the cart. Refresh the page and ensure the removed product does not reappear. | User Name: Test1 Pwd: Test1@2025 | Removed item should no longer be visible in the cart. | Item is removed and no longer appears in the cart list. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify shopping cart functionality. | TC0037 | Verify that the total price updates correctly when items are added/removed. | Navigate to the Demoblaze website homepage. Add multiple products to the cart by clicking "Add to Cart" on their details pages. Open the Cart page and note the total price. Remove one product from the cart. Verify that the total price updates correctly based on the remaining items. Add another product and confirm that the total price recalculates accordingly. Refresh the page and ensure the total price remains accurate. | User Name: Test1 Pwd: Test1@2025 | Total price should adjust accurately based on the cart items. | Total price recalculates and displays correctly after each add/remove action. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify shopping cart functionality. | TC0038 | Verify that adding/removing items from the cart is processed without delays. | Navigate to the Demoblaze website homepage. Select a product and click "Add to Cart" on the product details page. Verify that the confirmation message appears promptly without noticeable delay. Open the Cart page and ensure the added product appears instantly. Click the "Remove" or "Delete" button for an item in the cart. Verify that the item is removed immediately without delays. Repeat the process with multiple products to ensure consistent performance. | User Name: Test1 Pwd: Test1@2025 | Add/remove actions should reflect immediately without performance lag. | Cart updates instantly with no delay or lag. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify checkout and order placement functionality. | TC0039 | Verify that clicking on the “Place Order” button opens the order form. | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page. Click on the "Place Order" button. Verify that the Order Form appears with input fields for customer details (e.g., Name, Country, City, Credit Card, etc.). Ensure the form loads properly without delays or errors. | User Name: Test1 Pwd: Test1@2025 | Clicking the button should display the checkout form with input fields. | Checkout form opens with all required fields visible. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify checkout and order placement functionality. | TC0040 | Verify that users can enter details (name, country, city, credit card, month, year). | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page. Click on the "Place Order" button to open the order form. Verify that the following input fields are available and editable: Name Country City Credit Card Month Year Enter valid details in each field and confirm that text is accepted without errors. Ensure that users can navigate between fields smoothly. | User Name: Test1 Pwd: Test1@2025 | All user inputs should be accepted in the respective fields. | All fields accept valid input values as expected. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify checkout and order placement functionality. | TC0041 | Verify that the order form validation prevents submitting empty fields. mandatory fields display validation messages when left empty | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page. Click on the "Place Order" button to open the order form. Leave all fields (Name, Country, City, Credit Card, Month, Year) empty. Click on the "Purchase" button. Verify that validation messages appear for the required fields. Ensure that the form does not submit until all mandatory fields are filled. Enter valid details and check that the validation messages disappear. | User Name: Test1 Pwd: Test1@2025 | System should prevent form submission and show error messages for empty mandatory fields. | Empty fields trigger validation and display appropriate error messages. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify checkout and order placement functionality. | TC0042 | Verify that clicking “Purchase” places the order and displays a success message. | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page. Click on the "Place Order" button to open the order form. Enter valid details in all required fields (Name, Country, City, Credit Card, Month, Year). Click on the "Purchase" button. Verify that an order confirmation message appears (e.g., "Thank you for your purchase!"). Ensure that an Order ID or purchase details are displayed in the success message. Check if there is an option to OK/Close the confirmation message and return to the homepage. | User Name: Test1 Pwd: Test1@2025 | Order should be placed and a success/confirmation message should appear. | “Thank you for your purchase” message displays after clicking Purchase. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify payment processing and order confirmation. | TC0043 | Verify that valid credit card details allow a successful purchase. | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page. Click on the "Place Order" button to open the order form. Enter valid details in all required fields: Name Country City Credit Card (valid card number) Month Year Click on the "Purchase" button. Verify that the order is processed successfully and a confirmation message appears (e.g., "Thank you for your purchase!"). Check if the Order ID or purchase details are displayed in the success message. Ensure that no validation errors appear when using a valid credit card. | User Name: Test1 Pwd: Test1@2025 | Valid credit card input should be accepted and order should be processed. | Valid credit card details accept and purchase completes successfully. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify payment processing and order confirmation. | TC0044 | Verify that invalid credit card details show an error message. | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page. Click on the "Place Order" button to open the order form. Enter valid details in all required fields except for the Credit Card, and use invalid data such as: Empty credit card field Random numbers (e.g., 1234 5678 9012 3456) Less than the required number of digits Special characters or letters Click on the "Purchase" button. Verify that an error message appears (e.g., "Invalid credit card number. Please enter a valid card."). Ensure that the order is not processed and no confirmation message appears. Enter a valid credit card number and confirm that the error message disappears, allowing a successful purchase. | User Name: Test1 Pwd: Test1@2025 | Invalid card inputs should trigger an error and block the transaction. | System displays an error message when invalid credit card info is submitted. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify payment processing and order confirmation. | TC0045 | Verify that after a successful payment, the cart is emptied automatically. | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page and verify that the selected product(s) are listed. Click on the "Place Order" button to open the order form. Enter valid details in all required fields (Name, Country, City, Credit Card, Month, Year). Click on the "Purchase" button. Verify that a success message appears (e.g., "Thank you for your purchase!"). Close the confirmation message and navigate back to the Cart page. Verify that the cart is now empty and no previously purchased items remain. Refresh the page and ensure that the cart remains empty. | User Name: Test1 Pwd: Test1@2025 | Cart should be cleared immediately after successful order placement. | Cart clears automatically after placing the order. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Cart | To verify payment processing and order confirmation. | TC0046 | Verify that an order confirmation pop-up appears after a successful transaction. | Navigate to the Demoblaze website homepage. Add at least one product to the cart by clicking "Add to Cart" on the product details page. Open the Cart page and verify that the selected product(s) are listed. Click on the "Place Order" button to open the order form. Enter valid details in all required fields (Name, Country, City, Credit Card, Month, Year). Click on the "Purchase" button. Verify that an order confirmation pop-up appears with details such as: "Thank you for your purchase!" message Order ID Total amount paid Ensure that the pop-up has a "OK" or "Close" button. Click on "OK" and verify that the pop-up closes successfully. | User Name: Test1 Pwd: Test1@2025 | A pop-up/modal should confirm successful order with summary details. | Order confirmation pop-up appears with product and price details. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | N/A | Vijay
General Login | Demoblaze | Entire Website | To verify security aspects of the application. | TC0047 | Verify that SQL injection attacks are not possible in input fields (username, password, search). | Navigate to the Demoblaze website homepage. Locate the Login form and enter SQL injection payloads in the Username and Password fields, such as: ' OR 1=1 -- admin' -- admin' # admin' OR '1'='1' admin' UNION SELECT NULL, NULL, NULL -- Click on the "Log in" button and verify that the login fails with an appropriate error message (e.g., "Invalid username or password."). Navigate to the Search bar and enter SQL injection payloads such as: ' OR 1=1 -- '; DROP TABLE users; -- '; SELECT * FROM products WHERE name LIKE '%laptop%' -- Click on the Search button and verify that: No unexpected data is retrieved. No database errors are displayed. The website functions normally. Repeat steps for other input fields (e.g., Registration form, Order form) to check if SQL injection is possible. Confirm that the application properly sanitizes inputs and uses prepared statements to prevent SQL injection. | UserName: Test02 Pwd: Test02@2025 | ✅ The application should not accept SQL injection payloads. ✅ No unauthorized access or data leakage should occur. ✅ Proper validation and error handling should be in place. | Injected SQL payload in username, password, and search fields is rejected. System handles input safely and login/search behavior remains unaffected. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | This test case is out of scope for the current UI-only demo application. However, it is added additionally to highlight basic client-side security validations and raise awareness about common vulnerabilities like SQL injection and XSS. | Vijay
General Login | Demoblaze | Entire Website | To verify security aspects of the application. | TC0048 | Verify that cross-site scripting (XSS) attacks are prevented in input fields. | Navigate to the Demoblaze website homepage. Identify input fields where user input is accepted, such as: Username (Login/Signup) Password Search bar Contact form (if available) Order form fields (Name, Country, City, etc.) Enter common XSS payloads in each input field, such as: <script>alert('XSS')</script> "><script>alert('XSS')</script> <img src="x" onerror="alert('XSS')"> <iframe src="javascript:alert('XSS')"></iframe> Submit the form or execute the input by: Clicking Login, Register, or Search Submitting the Contact or Order form Observe the response and verify that: The script is not executed. No alert box or injected script runs. The input is either sanitized or an error message is displayed. Check if the input is reflected anywhere on the webpage (e.g., error messages, profile, confirmation messages). Inspect the page source code (Right-click → View Page Source) and check if the script is stored and rendered. Ensure that the application properly escapes special characters and uses input validation to prevent XSS. | UserName: Test02 Pwd: Test02@2025 | The application should not execute any JavaScript entered in input fields. ✅ The input should be sanitized or rejected if it contains script tags. ✅ No unauthorized access, pop-ups, or modifications should occur. | Script tags like <script>alert('XSS')</script> input into forms are treated as plain text and do not execute. No alert or code execution occurs. | Pass | 2025-06-21 | 2025-06-22 | N/A | First | This test case is out of scope for the current UI-only demo application. However, it is added additionally to highlight basic client-side security validations and raise awareness about common vulnerabilities like SQL injection and XSS. | Vijay

## Defect Sheet
User Type | App Name | Functionality | Test Case ID | Defect ID | Defect Desc | Steps to Reproduce | Expected Result | Status (Open/Closed/Hold) | Priority | Severity | Raised On | Closed On | Iteration | Remark | Developer Name | Developers Comment (If Any)
General Login | Demoblaze | Sign up | TC0002 | D0001 | System is allowing to register with an existing username eventhough the same username present in the system with active status. | Navigate to the Demoblaze website. Click on 'Sign up' button. Enter an existing username. Enter a valid password. Click on the 'Sign up' button. Verify that an error message appears. | When a user tries to register with an already existing username, the system should display a clear message like: “Username already exists. Please choose a different one.” | Closed | High | High | 2025-06-23 | 2025-06-24 | First | N/A | Siddharth | It’s a Defect. The Defect has been closed now.
General Login | Demoblaze | Sign up | TC0003 | D0002 | System is not allowing registration with an existing username (which is correct), but instead of showing a proper error message, it displays only a generic message: 'Error' in red | Navigate to the Demoblaze website. Click on 'Sign up' button. Leave the username field blank. Enter a valid password. Click on the 'Sign up' button. Verify that an error message appears. | System should not allow to register with an error "Username and password should not be blank". | Closed | Medium | Medium | 2025-06-23 | 2025-06-24 | First | N/A | Siddharth | It’s a Defect. The Defect has been closed now.
General Login | Demoblaze | Home | TC0026 | D0003 | In the category section, only the 'Phones' category is displayed three times. 'Laptops' and 'Monitors' categories are missing | Navigate to the Demoblaze website homepage. Locate the product categories section. Verify that the following categories are displayed: Phones Laptops Monitors Click on each category and ensure that relevant products are displayed correctly. Check that product images, names, and prices are visible and properly aligned. | Category section should show all three categories: Phones, Laptops, and Monitors. | Closed | High | High | 2025-06-23 | 2025-06-24 | First | N/A | Siddharth | It’s a Defect. The Defect has been closed now.
General Login | Demoblaze | Product | TC0030 | D0004 | Product description does not change according to the selected product. The same description appears for all products, while name, image, and price are correctly displayed | Navigate to the Demoblaze website homepage. Click on any product to open the product details page. Verify that the following details are correctly displayed: Product Name Product Image Price Description Ensure that the details match the selected product. Check that the image is clear, properly aligned, and not broken. | Product details page should show the correct name, image, price, and description of the selected product. | Closed | Medium | High | 2025-06-23 | 2025-06-24 | First | N/A | Siddharth | It’s a Defect. The Defect has been closed now.
General Login | Demoblaze | Cart | TC0033 | D0005 | After clicking on 'Add to Cart', the system shows a success message and updates the cart counter (e.g., '1'), but the product details do not appear on the cart page. | Navigate to the Demoblaze website homepage. Click on a product to open its product details page. Click the "Add to Cart" button. Verify that a confirmation message appears (e.g., "Product added to cart successfully."). Open the Cart page and check if the added product is listed correctly with the correct name, price, and quantity. | Product should be added to the cart and listed with its name and price. | Closed | High | High | 2025-06-23 | 2025-06-24 | First | N/A | Siddharth | It’s a Defect. The Defect has been closed now.

## Test Summary Report
App Name | Iteration (First/Second) | As Of Date | Total Test Cases | Total Cases Executed | Total Pass Cases | Total Fail Cases | Total Hold Cases | Total Open Defects | Total Closed Defects | Total Hold Defects | Total Observations (Not Defects)
Demoblaze | First | 2025-06-23 | 48 | 48 | 43 | 5 | 0 | 5 | 0 | 0 | 0
Demoblaze | First | 2025-06-25 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0